Build Plan v2

Open-source AI content engine — authenticity-first, power-user, multi-audience

14 months · 28 sprints · AGPL core + hosted product · validated April 2026

# 0. Strategic positioning

## 0.1 What this product is

An open-source, multi-tenant AI content engine for technical creators who want to publish across social platforms without losing their voice to AI generic-ness. Hosted product available for non-technical creators and teams. Architecturally and philosophically built to respect the creator's authenticity and their automation tooling — not to maximize engagement-bait output.

## 0.2 Six product principles

Every product decision over 14 months runs through these. If something violates a principle, it doesn't ship — even if a competitor does it.

- Voice over volume. We help users sound more like themselves, not less.

- Authenticity over engagement. We do not optimize for hooks, hashtag stuffing, or AI-tell-tales.

- Transparency over magic. Every AI change is visible, diff-able, and reversible.

- Ownership over lock-in. Open-source core, BYO keys, no vendor capture.

- Power-user respect. Real APIs, real webhooks, real automation — not toy integrations.

- Build in public. The product story is told as it's lived, not as a marketing campaign.

## 0.3 Audiences

Three audiences are served by the same multi-tenant platform. Each is a tenant template (a default workspace configuration), not a separate product. The plan leads with individual creators because that's where Phase 1 marketing energy concentrates; the other two are explicitly supported but not the homepage hero.

| Audience | Posture | Phase 1 priority | Marketing | Tenant template |
| --- | --- | --- | --- | --- |
| Individual creators (PRIMARY) | Power-user, technical, values authenticity | Headline audience — homepage speaks here | Lead all messaging; dev-community + content marketing | 'Solo Creator' WS template |
| SMBs (SECONDARY) | Operations-minded, want approval workflows + brand control | Supported via tenant templates + approval workflows in P2 | Mentioned in pricing page; case studies in P2 | 'Small Business' WS template |
| Faith communities (SECONDARY) | Volunteer-driven, multilingual, community-serving | Supported via tenant templates; Arabic/Spanish/Hebrew packs in P3 | Soft-launch in P2; community-led growth | 'Community Org' WS template |

## 0.4 Differentiation moat

Five compounding advantages that together create a position Blotato cannot easily match without strategic reinvention. These are the source of the answer to the question 'why would anyone pick this over Blotato.'

| Differentiator | What it means | How it shows up in the build | Why Blotato can't easily copy |
| --- | --- | --- | --- |
| Open-source core (AGPL) | Engine, adapters, schemas all OSS; hosted product is the proprietary monetization | Public repo from S01; all code under AGPL; hosted-only features clearly fenced | Would require rebuilding; AGPL is one-way; community trust accumulates over time |
| Authenticity Engine | Voice profiles, anti-slop guards, AI-tell removal — built into the remix engine | First-class feature from S04–S05; not bolted on | Their entire brand is volume-first ('1 week in 1 minute'); incompatible reposition |
| API + MCP first-class | Public API, MCP server, n8n+Make nodes ship in P1, not P2 | S04 ships API v1; S11 ships MCP; S12 ships nodes | They have these but they're afterthoughts; we're built around them |
| BYO-key model | Power users supply their own AI keys, escape per-credit billing | S17 ships BYO keys; flat hosted pricing | Their business model relies on credit metering; hard to walk back |
| Build-in-public + Autonomy Gap | 5–10 hrs/week of authentic content marketing tied to a values-based YouTube channel | Marketing isn't a launch event; it's a 14-month continuous activity | Their distribution depends on one founder's personal channel; ours is values-aligned |

## 0.5 Honest competitive read

This is a head-on competitive play, not a niche wedge. Blotato has a creator with 1.5M+ followers as its founder-led marketing engine and a 12-18 month head start. The expected outcome is slower revenue ramp than the faith-wedge alternative would have produced, with a higher ceiling if the open-source + power-user strategy compounds. First 100 paying customers will be hard. First 1,000 will be much easier if the OSS adoption signal is real.

What success looks like at month 6: OSS repo with 500–2,000 GitHub stars, 50–150 paying hosted customers, 5–15 self-host installs we know about, weekly Autonomy Gap content cadence, organic dev-community presence.

What failure looks like: Generic Blotato clone with no OSS traction, single-digit paying customers, content marketing abandoned by month 3. If we hit failure signals, the documented pivot is to lean harder into the API-first dev-tool angle and reduce hosted UI investment.

# 1. Phase roadmap

| Phase | Months | Sprints | Theme | Ship gate |
| --- | --- | --- | --- | --- |
| Phase 1 — Core + API + Voice | 1–6 | 1–12 | OSS launch, multi-tenant publisher with Authenticity Engine, public API, MCP server, n8n+Make nodes | Public OSS release + paid hosted: $19 Free-OSS / $49 Solo / $129 Studio |
| Phase 2 — Video + Power-User Depth | 7–10 | 13–20 | Faceless video, long-to-short clipper, advanced API, BYO-key flows, approval workflows, OSS adoption push | Launch $249 Pro tier with video + advanced API |
| Phase 3 — Agency, Mobile, Full Platform Set | 11–14 | 21–28 | All 9 platforms, unified inbox, translation, content vault, link-in-bio, mobile PWA, agency multi-tenant features | Launch $599 Agency tier |

### Phase 1 — Core + API + Voice (months 1–6)

Multi-tenant SaaS with OSS core. Five-platform publishing (X, LinkedIn, Facebook, Instagram, TikTok). Authenticity Engine (voice profiles, anti-slop guards). Public REST API and MCP server ship in P1, not later — they are the differentiation, not extras. Brand kits, carousels, draft refinement chat. Open-source repo public from Sprint 1; AGPL license; build-in-public from day 1. Ships paid hosted product alongside OSS launch.

### Phase 2 — Video + Power-User Depth (months 7–10)

Faceless AI video generation, long-to-short clipper, voice cloning. BYO-key infrastructure (customers supply their own AI keys to escape per-credit billing). Advanced webhooks with replay-safe signing. Approval workflows. Content Vault foundations with pgvector. OSS adoption push: contributor program, public roadmap, dev-community campaign.

### Phase 3 — Agency, Mobile, Full Platform Set (months 11–14)

Four more platforms (YouTube, Pinterest, Threads, Bluesky) bring total to 9. Unified inbox with AI triage and voice-locked drafted replies. Translation pipeline. Mobile PWA composer. Content Vault v2 with semantic search. Link-in-bio builder (also OSS). Thumbnail A/B testing. Agency tier launch with white-label and advanced analytics.

# 2. Architectural diagram

Seven layers. Multi-tenant by workspace_id throughout. The new layer this version adds — the Authenticity Engine — sits between source ingestion and remix output, so voice preservation and anti-slop guards are baked into every generation, not bolted on top.

CLIENT — open-source UI + hosted dashboard + composer

| Web App (OSS) Next.js 15 Self-host or hosted Workspace model | Mobile Composer PWA in P2 Native iOS/Android P3 | Auth + Workspaces Supabase Auth Multi-workspace Tenant-aware | Stripe Billing Hosted-only Flat tiers BYO-key bypass |
| --- | --- | --- | --- |

▼

API LAYER — public-first by design

| Public REST API v1 from S04 Versioned + stable OpenAPI spec | MCP Server First-class Claude / Cursor / IDE Ships in P1 | Webhooks Outbound events Signed payloads Replay protection | n8n + Make Nodes Official Community-maintained Ships in P1 | Internal API UI-driven routes Same primitives as public |
| --- | --- | --- | --- | --- |

▼

AUTHENTICITY ENGINE — the philosophical differentiator

| Voice Profile Learns from past posts Per-workspace fingerprint Style preservation | Anti-Slop Guards Cliché detection Generic phrase filters AI tell-tale removal | Source Fidelity Preserves user voice Annotates AI changes Diff-aware editing | Refinement Chat Conversational edits Voice-locked Tracks every change |
| --- | --- | --- | --- |

▼

ASYNC JOB LAYER — Trigger.dev v3

| Ingestion yt-dlp + Whisper Trafilatura PDF + docs | Remix Engine Voice-aware prompts Multi-model router BYO-key support | Image + Carousel Replicate + Flux Slide generator Brand-locked styling | Video Engine (P2) Faceless video Long→short clipper Voice + caption | Publisher Adapter routing Retries + backoff Token refresh | Inbox + Trends (P3) Comments + DMs AI triage Best-time calc |
| --- | --- | --- | --- | --- | --- |

▼

PLATFORM ADAPTERS — 9 channels

| X / Twitter v2 · pay-per-use | LinkedIn UGC + Page | Facebook Pages + Groups | Instagram Feed/Reels/Carousel | TikTok Direct + inbox | YouTube Shorts + long | Threads Meta API | Pinterest Pin + Idea | Bluesky AT Protocol |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

▼

INTELLIGENCE LAYER — analytics, vault, agency

| Analytics Pipeline Per-post metrics Voice-fit scoring Best-time calc | Content Vault Semantic search Voice training corpus Cross-WS reuse | Approval Workflow Draft → Review Diff + comments Roles per WS | Translation (P3) DeepL + Claude polish Per-region schedule | Link-in-Bio (P3) Hosted page Open-source theme |
| --- | --- | --- | --- | --- |

▼

DATA & STORAGE — multi-tenant from day 1

| Postgres (Supabase) RLS by workspace_id Self-host: own DB pgvector for vault | Redis (Upstash) Rate limits per WS Job dedupe Hot session cache | S3 + CloudFront Self-host: any S3 WS-namespaced keys CDN URLs | Search + Vectors pgvector for vault Voice fingerprints Embedding store |
| --- | --- | --- | --- |

# 3. Open-source strategy

Open source is core to the differentiation. This is the GitLab / Cal.com / Plausible model: AGPL core that anyone can self-host, proprietary hosted product that funds development, commercial license available for enterprises that can't accept AGPL.

## 3.1 What's open vs closed

| Component | License | Hosted-only? | Notes |
| --- | --- | --- | --- |
| Core engine (ingestion, remix, AI router) | AGPL-3.0 | No | Anyone can self-host. AGPL prevents SaaS competitors from forking without contributing back |
| Platform adapters | AGPL-3.0 | No | Critical to OSS value — community can contribute new platforms |
| Public REST API + MCP server | AGPL-3.0 | No | Standardizes the interface; encourages ecosystem |
| n8n + Make nodes | MIT | No | Looser license to maximize adoption (n8n is itself MIT) |
| Authenticity Engine (voice profiles, anti-slop) | AGPL-3.0 core / proprietary models | Partial | Code is OSS; trained voice models are hosted-only |
| Web UI | AGPL-3.0 | No | Self-hosters get the same UI; lowers our marketing burden |
| Hosted infrastructure (queues, S3 layer) | AGPL-3.0 | No | Documented; self-hosters wire their own |
| Hosted-only features | Proprietary | Yes | Approval workflows, agency multi-tenant management, advanced analytics, white-label, support |

## 3.2 Why AGPL specifically

AGPL-3.0 is chosen deliberately because it's the only OSS license that prevents a competitor (including a well-funded incumbent) from forking the code and offering it as a competing SaaS without contributing changes back. MIT or Apache would let Blotato fork and ship; AGPL effectively prevents that. The trade-off is some enterprises will not accept AGPL — they get a commercial license tier in Phase 3.

## 3.3 Operating the open-source project

- Public GitHub repo from Sprint 1. Initial commits are real, not a 'big bang' release

- Public roadmap (GitHub Projects or Linear public)

- Issues triaged weekly; community contributors welcomed from day 1

- Contributor License Agreement (CLA) required so we retain the right to dual-license

- Documentation site (Mintlify or Docusaurus) public from Sprint 2

- Discord or Discourse for community; Discord for speed, Discourse if we want indexable knowledge

- Self-host docs are first-class — not an afterthought

- Versioned releases on a regular cadence (every 2–4 weeks)

- Contributor recognition: README hall-of-fame, optional revenue share for major features later

## 3.4 Hosted vs self-hosted feature matrix

- All ingestion, remix, image gen, video gen, publishing, scheduling: OSS — works self-hosted

- All platform adapters: OSS — works self-hosted

- Public API + MCP server: OSS — works self-hosted

- Approval workflows: hosted-only (or available with commercial license)

- Agency multi-tenant management: hosted-only

- Advanced analytics with cross-WS comparisons: hosted-only

- White-label / custom domain: hosted-only

- SLAs and customer support: hosted-only

- Trained voice models (the actual ML weights): hosted-only

# 4. The Authenticity Engine

The most important new system in this plan. Sits in the remix pipeline; activates between source ingestion and platform-specific output. Four subcomponents:

## 4.1 Voice Profile

- Per-workspace fingerprint built from the user's past published posts (provided at onboarding or learned over time)

- Captures: typical sentence length distribution, vocabulary richness, common openers, punctuation patterns, emoji usage, formality register, hashtag conventions

- Stored as structured features + a small trained classifier; not just an embedding

- Used as a constraint in every remix prompt: 'Generate this in a voice consistent with these features'

- User can edit, lock, or disable the voice profile per draft

## 4.2 Anti-Slop Guards

A library of detectors that flag AI-generic phrases and patterns before output ships. Not a single LLM check — a deterministic filter pass plus an LLM judge. Examples of what it catches:

- Cliché AI openers: 'In today's fast-paced world…', 'Let's dive in', 'Here's the thing…'

- Hedged commitment phrases: 'It's worth noting that…', 'It's important to remember…'

- Empty intensifiers and vague qualifiers: 'incredibly', 'truly', 'absolutely'

- Hashtag-stuffing patterns

- Em-dash overuse and other AI tell-tales

- Generic hook formulas that don't match the user's voice profile

Output: each detected pattern shows in the draft as a highlighted suggestion the user can accept (rephrase) or reject. Not silently rewritten — visible.

## 4.3 Source Fidelity

- Tracks the diff between user's source content and AI-generated output

- Highlights what changed; the user can revert any change with one click

- Distinguishes 'paraphrase' (low risk) from 'invented detail' (high risk; requires user verification)

- Annotates the final draft with a confidence/fidelity score

## 4.4 Refinement Chat

- Conversational editing of a draft, with the voice profile as a hard constraint

- Every chat turn is recorded; each version of the draft is retrievable

- User can lock specific phrasing ('don't change this sentence') and the model respects it

- Built on Claude Sonnet by default; BYO-key in Phase 2

# 5. Sprint plan (28 sprints / 56 weeks)

Two-week sprints. Cowork column shows primary working mode: 🤖 Cowork-ready, 🔀 Hybrid (human handles external systems), 👤 Human-driven.

| Sprint | Wks | Phase | Deliverable | Cowork |
| --- | --- | --- | --- | --- |
| S01 | 1–2 | P1 | Foundation: Next.js scaffold, Supabase, Stripe test, multi-tenant schema with workspace_id, RLS policies, deploy pipeline. Open-source repo public from day 1 (AGPL) | 🤖 |
| S02 | 3–4 | P1 | Workspace + RBAC: invite flow, roles, workspace switcher, seat-based billing scaffolding, public OSS docs site (Mintlify) | 🤖 |
| S03 | 5–6 | P1 | Source ingestion: yt-dlp worker, Whisper, Trafilatura, pdfplumber, file upload UI | 🤖 |
| S04 | 7–8 | P1 | Public REST API v1 + Voice Profile foundation: API keys per WS, OpenAPI spec, voice fingerprint extraction from past posts | 🔀 |
| S05 | 9–10 | P1 | Remix engine v1 + Authenticity Engine: voice-aware prompts, multi-model router (Claude/GPT/o3), anti-slop guards, BYO-key support | 🔀 |
| S06 | 11–12 | P1 | Brand Kit + draft refinement chat: per-WS brand kit, conversational draft editing with voice locking | 🤖 |
| S07 | 13–14 | P1 | AI Image + Carousel: Replicate Flux, aspect-ratio variants, multi-slide carousel generation, fix-text + remix | 🤖 |
| S08 | 15–16 | P1 | Media pipeline: presigned S3, FFmpeg on Modal, format compliance, CDN delivery, video transcoding for user uploads | 🤖 |
| S09 | 17–18 | P1 | Scheduler + content queue + bulk: cron scheduler, calendar UI, cadence rules, bulk CSV upload, drafts library | 🤖 |
| S10 | 19–20 | P1 | Twitter/X + LinkedIn adapters + X credit tracker: OAuth, publish, threads, pay-per-use cost ledger; submit LinkedIn dev portal app | 🔀 |
| S11 | 21–22 | P1 | Facebook + Instagram + MCP server v1: Meta App, OAuth, Reels + Carousel + Feed; SUBMIT META APP REVIEW; ship MCP server for Claude Desktop | 🔀 |
| S12 | 23–24 | P1 | TikTok + n8n/Make nodes + LAUNCH: Content Posting API, audit prep with inbox-fallback; n8n + Make community nodes; failed-post UX, onboarding, basic analytics, OSS LAUNCH + paid hosted launch | 🔀 |
| S13 | 25–26 | P2 | Video Engine v1: faceless video pipeline (script → AI images → ElevenLabs voice → captions → FFmpeg), 3 templates | 🔀 |
| S14 | 27–28 | P2 | Video Engine v2 + voice clone: more templates, voice cloning option, music bed, brand-kit injection | 🔀 |
| S15 | 29–30 | P2 | Long-form to short-form clipper: AI highlight detection, smart cropping for 9:16, auto-captions, batch export | 🔀 |
| S16 | 31–32 | P2 | API v2 + advanced webhooks: webhook signing, retries, replay-safe handlers, public webhook docs, dev playground | 🤖 |
| S17 | 33–34 | P2 | BYO-key infrastructure: customer-supplied Anthropic / OpenAI / Replicate keys, encrypted at rest, usage tracking & limits | 🤖 |
| S18 | 35–36 | P2 | Approval workflows + draft diffing: review → publish gating, comment threads on drafts, role-based gating | 🤖 |
| S19 | 37–38 | P2 | Voice training v2 + content vault foundation: pgvector for past posts, semantic search, repurpose-from-history flow | 🤖 |
| S20 | 39–40 | P2 | Pro tier launch + OSS adoption push: Pro billing, marketing + dev-community campaign, public roadmap, contributor program | 👤 |
| S21 | 41–42 | P3 | YouTube + Pinterest adapters: long + Shorts, Pin + Idea Pin, OAuth + publish flows | 🔀 |
| S22 | 43–44 | P3 | Threads + Bluesky adapters: thread-aware multi-platform composer, cross-posting smart-defaults | 🔀 |
| S23 | 45–46 | P3 | Unified inbox v1: comment + DM ingest from FB, IG, LinkedIn, X, YouTube; AI triage classification | 🤖 |
| S24 | 47–48 | P3 | Inbox v2: AI-drafted replies (voice-locked!), routing rules, response analytics | 🤖 |
| S25 | 49–50 | P3 | Translation pipeline + mobile PWA: DeepL + Claude polish, per-region scheduling, mobile composer PWA | 🤖 |
| S26 | 51–52 | P3 | Content Vault v2 + link-in-bio: semantic search UI, repurposing flows, hosted bio pages with custom domains | 🤖 |
| S27 | 53–54 | P3 | Thumbnail A/B + best-time advanced: video thumbnail generation + rotation, advanced posting time analytics | 🤖 |
| S28 | 55–56 | P3 | Agency polish + launch: white-label, client report exports, advanced analytics, AGENCY TIER LAUNCH | 🔀 |

## 5.1 Phase gates (non-negotiable)

- End of Sprint 12 (month 6): OSS public release + paid hosted launch. 5 platforms, Authenticity Engine, public API, MCP server, n8n+Make nodes all live. Free-OSS / $49 Solo / $129 Studio tiers active.

- End of Sprint 20 (month 10): Pro tier with video + BYO-key. Public roadmap, contributor program, dev-community campaign live. If OSS metrics (stars, contributors, self-host installs) are weak, pivot to API-first dev-tool focus before Phase 3.

- End of Sprint 28 (month 14): Agency tier launch. 9 platforms, inbox, vault, translation, link-in-bio, mobile PWA. Commercial license offering for enterprises.

# 6. Distribution plan (5–10 hrs/week, all 14 months)

Distribution is not a launch event. It's a 14-month continuous activity that runs alongside the build. Without it, the head-on competitive strategy fails — there's no path to first 100 customers without a distribution engine for an open-source-first product against a 1.5M-follower incumbent.

| Channel | Cadence | Goal | Time/wk |
| --- | --- | --- | --- |
| Autonomy Gap YouTube | 1 video / 2 wks | Authority + audience growth; tie content philosophy to product story | 3 hrs |
| Build-in-public on X + LinkedIn | 3–5 posts/wk | Show the work; attract dev/creator audience; authentic content as marketing for content tool | 2 hrs |
| Open-source presence (GitHub, HN, Indie Hackers) | 1 milestone post / wk | Community formation; OSS contributor recruitment; trust signal | 1.5 hrs |
| Customer interviews (P1) / community calls (P2+) | 2–3 calls/wk | Continuous customer research; content fuel | 2 hrs |
| Dev community engagement (Reddit, dev.to, n8n / MCP forums) | Async, daily check-in | Niche authority; product feedback; bug reports as marketing | 1.5 hrs |

## 6.1 Build-in-public approach

- Repo public from S01. First commit, first README, first issue all visible

- Weekly milestone post on X, LinkedIn, GitHub Discussions

- Sprint reviews public — show what shipped, what didn't, what's next

- Customer interviews summarized publicly (with permission) as content

- Mistakes and pivots posted honestly — the audience for an authenticity-first tool rewards authenticity from its founder

## 6.2 Autonomy Gap as a marketing asset

Your existing YouTube channel is already a values-aligned platform. Continue producing channel-native content (psychology, autonomy, manipulation dynamics) — but layer in product-relevant videos that connect the philosophy to the tool. Examples:

- 'Why AI content sounds AI' — the slop problem, broadly

- 'I scanned 100 LinkedIn posts. Here's what AI tells on'

- 'Building a content tool that doesn't make you sound generic' — the build journey

- 'Open-source vs closed-source AI tools' — the trust angle

## 6.3 Dev-community presence

- Indie Hackers — milestone posts, revenue updates, build journey

- Hacker News — major releases (Show HN: ...), thoughtful long-form

- dev.to / Hashnode — technical writeups (multi-tenant RLS deep-dive, Trigger.dev v3 in production, AGPL strategy)

- n8n community + Make community — when nodes ship, post in their forums

- MCP / Claude developer communities — when MCP server ships

- r/SideProject, r/SaaS — judiciously, when there's a real milestone

# 7. Operating costs

| Item | Type | P1 / 100 paying | P3 / 1,000 paying |
| --- | --- | --- | --- |
| Vercel (frontend + API) | Fixed | $50–150 | $300–500 |
| Supabase (DB + Auth + Storage) | Fixed | $25–100 | $400–800 |
| Trigger.dev v3 cloud | Fixed | $10–50 | $200–400 |
| Modal (Python media workers) | Variable | $50–200 | $800–2,000 |
| S3 + CloudFront | Variable | $30–100 | $400–1,200 |
| X/Twitter API (pay-per-use) | Variable | $50–150 | $500–1,500 |
| Sentry + Axiom + monitoring | Fixed | $60 | $200 |
| Email (Resend) | Fixed | $20 | $80 |
| Anthropic Claude (text) | Per WS | $50–300 total | $500–3,000 total |
| Replicate (images + video) | Per WS | $50–500 total | $800–8,000 total |
| ElevenLabs (P2+) | Per WS | $30–200 total | $400–3,000 total |
| BYO-key offset (savings!) | Negative | −$30 to −$100 | −$2,000 to −$8,000 |
| Stripe fees | % revenue | ~2.9% + $0.30/charge | Same |

### Margin analysis (revised for new pricing)

- P1 (~100 paying, ~$3,500 MRR mixed Solo+Studio): infrastructure + variable costs ≈ $700–1,800; net contribution $1,500–2,800/mo

- P2 (~250 paying, ~$15,000 MRR with Pro tier and BYO-key): costs $1,500–4,000; net contribution $9,500–13,000

- P3 (~1,000 paying, ~$70,000 MRR with Agency tier): costs $5,000–18,000; net $50,000–65,000

Note on BYO-key pricing: BYO-key plans cost LESS to operate but should not be priced as discounts. Price them at the actual support + hosting cost ($29-39/mo flat). Power users will pay this happily because it's still cheaper than their previous credit-burn while preserving full control.

# 8. Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Head-on competition with Blotato | Certain | High | Differentiate hard on philosophy + OSS + power-user; don't try to match feature-for-feature |
| OSS doesn't drive expected adoption | Medium | High | Track GitHub stars, contributors, self-host instances by S20; pivot to dev-tool focus if signals weak |
| Distribution time eats build time | High | High | Hard rule: 5–10 hrs distro is a CEILING not a floor; if build slips two sprints, cut distro to 3 hrs |
| AGPL scares enterprise customers | Medium | Medium | Offer commercial license tier in P3 for enterprises that need it |
| BYO-key reduces hosted revenue | High | Medium | Price BYO-key plans for the actual support cost; not a discount |
| Voice profile quality disappoints | Medium | High | Ship voice profile as opt-in beta in P1; iterate against real user posts; don't over-promise |
| Burnout over 14 months | High | Critical | Hard 4hr/day build rule; one full day/wk off; pause if shipping degrades |
| Meta / TikTok review delays | High | High | Submit by S11 / S12; have launch plan that works without them (ship 3 platforms first if needed) |
| Forks become real competitors | Low | Medium | AGPL prevents SaaS forks; commercial features stay proprietary; community focus stays on contributing back |
| Cowork generates code that violates AGPL boundaries | Low | High | CLAUDE.md spells out OSS / proprietary boundaries; CI gate on license headers |

# 9. Tech stack (locked)

- Frontend: Next.js 15 App Router, Tailwind, shadcn/ui, TypeScript strict. PWA wrapper for mobile in Sprint 25.

- Backend: Next.js Route Handlers; separate Node worker service for jobs (Trigger.dev v3).

- Database: Supabase (Postgres + Auth + Storage). pgvector for content vault and voice embeddings. RLS on every table.

- Job queue: Trigger.dev v3 — Bun-based long-running workers; no serverless timeout issues.

- Heavy workers: Modal for FFmpeg, Whisper, yt-dlp, video assembly.

- Payments: Stripe with metered billing for credit overages; flat tiers for BYO-key plans.

- Auth: Supabase Auth with email + Google + GitHub providers.

- Monitoring: Sentry, Axiom, Stripe webhook log table.

- Media: S3 + CloudFront. Workspace-namespaced keys (s3://bucket/ws/{workspace_id}/...).

- AI providers: Anthropic (primary), OpenAI (model picker), Replicate (images + video), ElevenLabs (voice), DeepL + Claude (translation).

- Docs: Mintlify for hosted docs; same content open-source.

# 10. Decisions still open

- S01 — Product name. Not 'AI Content Engine'. Recommend something short, ownable, vaguely literary or technical. Suggest committing by S03.

- S02 — CLA tooling. CLA Assistant (free) vs EasyCLA. Recommend CLA Assistant.

- S04 — Default text model. Claude Sonnet vs router. Recommend Claude Sonnet default.

- S05 — Voice profile architecture. Pure prompt engineering vs small fine-tuned classifier. Recommend prompt engineering for P1, fine-tune in P2 if signal demands.

- S12 — Pricing tiers final. Recommend Free-OSS / $49 Solo (1 workspace, 5 socials) / $129 Studio (3 workspaces, 15 socials, BYO-key) for launch.

- S20 — Pro tier price. Recommend $249 with video + advanced API.

- S22 — Bluesky vs Mastodon priority. Recommend Bluesky first; Mastodon as community contribution.

- S28 — Commercial license pricing. Recommend custom-quote-only at launch; productize later.

# 11. Closing

This plan is a head-on competitive play with a sharp differentiation strategy. It's harder than the faith-wedge alternative and the expected revenue ramp is slower in months 1–6. The compensating strengths are real: an open-source moat that compounds, an authenticity-first philosophy that aligns with your existing audience and brand, and a power-user feature set that is genuinely defensible against an incumbent built around volume and credit-metering.

The plan succeeds if three things stay true:

- You ship the Authenticity Engine well in Phase 1. It's the philosophical claim that becomes a real product feature.

- OSS adoption signals are real by month 10 (stars, contributors, self-host installs). If they're not, pivot to API-first dev-tool focus.

- Distribution work happens every week, not in bursts. 5–10 hrs/week is real time, not aspirational.

Last word: the rewrite kept the technical architecture mostly intact because the architecture was sound — multi-tenant from day 1, Trigger.dev v3, Supabase with RLS, all of it. What changed is the ordering, the prioritization of API-first features into Phase 1, the addition of the Authenticity Engine as a first-class system, and the explicit OSS strategy. The 14 months are real. Build it.